## Sheet1
[5 empty] | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Planned Velocities | Actual Velocities | Total Planned Story Points | Total Completed Story Points
[5 empty] | Goal: MVP, front-end only |  |  | Goal: AI impl |  |  | Goal: Impl Networked Multiplayer |  |  | Goal: Finish Impl. Networked Multiplayer |  |  | Goal: Connect frontend to backend |  |  | Goal: Refinement of product |  |  | 159 | 129 | 159 | 129
[5 empty] | Start = Feb. 28, End = Mar. 6 |  |  | Start = Mar. 7, End Mar. 13 |  |  | Start = Mar. 14, End Mar. 20 |  |  | Start = Mar. 28, End Apr. 3 |  |  | Start = Apr. 4, End Apr. 10 |  |  | Start = Apr. 25, End May 1 |  |  | 184 | 44 | 313 | 173
[5 empty] | Planned Vel. = |  | 159 | Planned Vel. = |  | 184 | Planned Vel. = |  | 172 | Planned Vel. = |  | 338 | Planned Vel. = |  | 239 | Planned Vel. = |  | 227 | 172 | 0 | 345 | 173
[5 empty] | Actual Vel. = |  | 129 | Actual Vel. = |  | 44 | Actual Vel. = |  | 0 | Actual Vel. = |  | 206 | Actual Vel. = |  | 239 | Actual Vel. = |  | 175 | 338 | 206 | 511 | 379
Short Title | Theme | Kano Category | Story Points | Priority | Pri | In | Done | Pri | In | Done | Pri | In | Done | Pri | In | Done | Pri | In | Done | Pri | In | Done | 239 | 239 | 618 | 618
Main Epic User Story | Epic | Mandatory | 845 | 1 | [18 empty] | 227 | 175 | 845 | 793
Choose game type | Front-End Interface | Mandatory | 10 | 4.0601 | 4.0601 | X | X
Game start | Front-End Interface | Mandatory | 40 | 1.015 | 1.015 | X | X
Player pairing cancellation | Front-End Interface | Exciter | 37 | 0.54866 | [12 empty] | 0.53718 | X | X
Visible “whose turn it is” | Front-End Interface | Mandatory | 13 | 3.1231 | 3.1231 | X | X
Column availability | Front-End Interface | Mandatory | 18 | 2.2556 | 2.2556 | X | X
Token placing | Front-End Interface | Mandatory | 25 | 1.7255 | 1.7255 | X | X
Visible game board | Front-End Interface | Mandatory | 23 | 1.9859 | 1.9859 | X | X
Final game results | Front-End Interface | Mandatory | 20 | 2.03 |  |  |  | 2.03 | X | X
End game options | Front-End Interface | Exciter | 13 | 1.7568 | [15 empty] | 1.7568 | X | X
Website URL and availability | Front-End Interface | Linear | 24 | 1.7974 |  |  |  | 1.7974 | X | X
AI implementation | Back-End Implementation | Exciter | 70 | 0.39876 |  |  |  | 0.39876 | X | [10 empty] | 0.39876 | X | X
Game logic turn implementation | Back-End Implementation | Mandatory | 30 | 1.3534 | 1.3534 | X |  |  |  |  | 1.3534 | X |  | 1.3534 | X |  | 1.3534 | X | X
Game logic record token drop implementation | Back-End Implementation | Mandatory | 65 | 0.62462 | [9 empty] | 0.61156 | X | X
Game logic win/lose/draw state detection | Back-End Implementation | Mandatory | 70 | 0.54376 |  |  |  | 0.54376 | X | [7 empty] | 0.54376 | X | X
Multiplayer pairing | Networking | Exciter | 77 | 0.42842 | [6 empty] | 0.42842 | X |  | 0.42842 | X |  | 0.42842 | X | X
Multiplayer game start | Networking | Mandatory | 25 | 1.827 | [6 empty] | 1.827 | X |  | 1.827 | X |  | 1.827 | X | X
Multiplayer game whose turn it is | Networking | Mandatory | 20 | 2.1569 | [6 empty] | 2.1569 | X |  | 2.1569 | X | X
Multiplayer record turn action | Networking | Mandatory | 20 | 2.03 | [6 empty] | 2.03 | X |  | 2.03 | X | X
Multiplayer game board state | Networking | Linear | 53 | 0.86181 | [9 empty] | 0.86181 | X | X
Multiplayer end-game state | Networking | Linear | 48 | 0.79298 | [9 empty] | 0.79298 | X | X
In-game emotes | Extra | Exciter | 47 | 0.48591 | [15 empty] | 0.48591 | X | X
In-game column emotes | Extra | Exciter | 52 | 0.43919 | [15 empty] | 0.43919 | X
Reactivity | Constraint | Mandatory
Multiplayer Phrase Pairing | Networking | Exciter | 45 | 0.62029 | [15 empty] | 0.62029 | X | X
Refactoring and Code Improvement | Constraint | Mandatory
|  |  | Retrospective: |  | Designing and implementing the front end was difficult at first, since it was my first time using the Yew framework. Was able to get a Minimum Viable Product front-end that should work as the base for future work on the front-end. |  |  | AI implementation was not as hard as I thought it would be. I initially gave it 100 points, but reduced it to 70. Admittedly, after implementing it, it still is somewhat flawed sometimes (as noticed during testing it), so it could be tweaked later, which is why the task isn’t complete, but incomplete. The resulting velocity is short of the planned velocity in this and the previous Sprint, but this is only because a single task in each Sprint is just shy of being complete. It appears to be over-commiting, but I don’t think that’s the case. |  |  | See the document in the “retrospectives” folder. |  |  | See the document in the “retrospectives” folder. |  |  | See the document in the “retrospectives” folder. |  |  | See the document in the “retrospectives” folder.
Note on D18: Reduced to 70 because figuring out the (start of) making Utility AI wasn’t too difficult.
Note on D23: Reduced to 25 because the non-multiplayer game-start is already working, so it shouldn’t be too hard to build off of that.
Note on D24: Reduced to 20 since the turn indicator already exists, so it shouldn’t be hard to update the turn indicator.
Note on D25: Reduced to 20 since the turn indicator exists. It shouldn’t be too hard to record turns in the record.
Note on K17: This was done on the side without realizing it was a task. Game is currently available at https://asdm.seodisparate.com/
Note on K18: AI could use some further improvement/tweaking, so it is still unfinished.
Note on K21: Was considered “DONE” in Sprint 2, but was revisited when the front-end was connected to the back-end in Sprint 5, so it is marked as “NOT DONE” in Sprint 2.
Note on M23: This task and the following two are related to the previous one. They may be implemented together at the same time.
Note on Q19: Depends on another task.
Note on Q20: This task wasn’t listed in Sprint 4’s Backlog, but upon inspection, it has been completed in this Sprint.
Note on Q22: Depends on another task.
Note on Q23: Depends on another task.
Note on Q26: This User Story (and the following one) happened to be completed in Sprint 4.
Note on AA1: Does not include User Stories in previous Sprints that were not completed.