## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
End Game Options
Front-end Reset Button Impl. | Done | 3 | 0
AI Implementation
AI fine tuning | Done | 3 | 3 | 3 | 0
In-game emotes
Back-end protocol update to support emote sending | Done | 1 | 1 | 1 | 1 | 1 | 0
Back-end protocol impl. to support emote sending | Done | 3 | 3 | 3 | 3 | 3 | 0
Front-end buttons to send emotes | Done | 3 | 3 | 3 | 3 | 3 | 0
Front-end display for received emotes | Done | 3 | 3 | 3 | 3 | 3 | 0
In-game column emotes
Back-end protocol update to support column emote sending | Pending | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Back-end protocol impl. to support column emote sending | Pending | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Front-end buttons to send column emotes | Pending | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Front-end display for received column emotes | Pending | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Multiplayer Phrase Pairing
Back-end protocol update to support phrase pairing | Done | 1 | 1 | 1 | 0
Back-end protocol impl. to support phrase pairing | Done | 3 | 3 | 3 | 0
Front-end GUI update to support phrase pairing | Done | 3 | 3 | 3 | 0
Reactivity (Constraint)
Refactoring and Code Improvement (Constraint)
Total Hours |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Hours Remaining |  | 33 | 30 | 30 | 20 | 20 | 10 | 10 | 10
Hours Completed |  | 0 | 3 | 3 | 13 | 13 | 23 | 23 | 23
Note on E1: No work on the project was done on Tuesday.
Note on G1: No work on tasks, only a refactoring/fix on this day.
Note on I1: Refactorings were done on this day.