## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Choose game type
Impl. Main menu | done | 2 | 2 | 2 | 2 | 2 | 0
Game start
Impl. Game start | done | 2 | 2 | 2 | 2 | 2 | 0
Visible “whose turn it is”
Impl. Turn indicator | done | 2 | 2 | 2 | 1 | 0
Column Availability
Impl. Column available indicator | done | 2 | 2 | 2 | 0
Visible game board
Impl. Front-end skeleton | done | 6 | 3 | 0
Impl. Front-end “game board” | done | 4 | 4 | 2 | 0
Impl. Players and colors | done | 2 | 2 | 2 | 0
Game logic turn implementation
Impl. Turn changer | Incomplete/Blocked | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Reactivity (constraint)
Total Hours Assigned |  | 17 | 17 | 20 | 20 | 20 | 22 | 22 | 22
Hours Remaining |  | 17 | 14 | 12 | 7 | 6 | 2 | 2 | 2
Hours Completed |  | 0 | 3 | 8 | 13 | 14 | 20 | 20 | 20
Note on B15: As mentioned in comment, may need to be reworked for multiplayer.
Note on C11: Was originally “3” here.
Note on D11: Took all of Monday to get a basic skeleton front-end working. EDIT: Ended up adding more, see next comment.
Note on E11: Added more to the front-end skeleton necessary for a proper app to work, such as connectivity between components and an output-text-box.
Note on F7: Side text indicates turn, but would be nicer to color-code the text as well.
Note on F9: Color-coded buttons indicate in the UI if it is an open slot.
Note on F12: Game board works as expected with the current implementation.
Note on F13: Support for the two player colors are implemented.
Note on F15: Implemented for the “local multiplayer” state, but may need to be reworked when implementing actual multiplayer.
Note on G7: Turn indicator has been made much more obvious.
Note on H3: Main menu was implemented, but allowing other game modes will be added once they are implemented (against AI and against networked player).
Note on H5: Game start implemented alongside main menu.