## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
AI Implementation
Basic interface to Utility AI | done | 1 | 0
Implement Utility AI | In Progress | 10 | 3 | 3 | 3 | 1 | 1 | 1 | 1
Update game to use AI | done | 3 | 3 | 3 | 3 | 0
Reactivity (constraint)
Game logic win/lose/draw state detection
Detect win state | done | 3 | 3 | 3 | 0
Detect draw state | done | 1 | 1 | 1 | 0
Indicate win/draw in gui | done | 3 | 3 | 3 | 0
Total Hours Assigned |  | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Hours Remaining |  | 14 | 13 | 13 | 6 | 1 | 1 | 1 | 1
Hours Completed |  | 0 | 8 | 8 | 15 | 20 | 20 | 20 | 20
Note on A7: AI testing can be difficult if there is no win/draw game logic implemented, so this story/task was added.
Note on D3: Setting up API wasn’t hard. The hard part is the implementation of AI...
Note on D4: The “backbone” of the Utility AI is done, just needs testing and tweaking.
Note on F8: Took some time, especially when writing the unit tests. Also added win indicators for win.
Note on G4: What’s left is tweaking the AI to work better.
Note on G5: AI takes their turn immediately, and I’m uncertain if there’s an easy way to pause the game for a brief moment before the AI makes their move.
Note on J4: Could still use some improvement/tweaking so this is left as “unfinished”.