## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Game Logic turn implementation
Implement turn changer | Pending | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Multiplayer Pairing
Front-end to Back-end protocol defined | In Progress | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Front-end async handling (figuring it out) | done | 3 |  | 0
Back-end database specification defined | In Progress | 3 |  |  |  |  | 1 | 1 | 1
Back-end minimum viable product impl | In Progress | 4 |  |  | 2 | 2 | 1 | 1 | 1
Front-end to Back-end connection impl | In Progress | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4
Multiplayer Game Start
Front-end and Back-end state sync | Pending | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Multiplayer game whose turn it is
Networked communication turn checking | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Multiplayer record turn action
Networked communication action checking | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total Hours Assigned |  | 21 | 21 | 24 | 28 | 28 | 31 | 31 | 31
Hours Remaining |  | 21 | 17 | 17 | 19 | 19 | 18 | 18 | 18
Hours Completed |  | 0 | 4 | 7 | 9 | 9 | 13 | 13 | 13
Note on A6: To figure out how to update the front-end asynchronously (for when making http requests to backend), an AI-take-turn-delay was implemented using async and javascript.
Note on A7: Added on Friday since back-end needs to use a database.
Note on A8: Added task since implementing the back-end wasn’t specified at the start of the sprint.
Note on D5: Initial “draft” of protocol created. Subject to future changes when back-end is implemented, which is why 1 hour is remaining for this task.
Note on G1: No work was done on this day, but work on Scrum management.