## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Game Logic turn implementation
Implement turn changer | In Progress | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1
Multiplayer Pairing
Front-end to Back-end protocol defined | done | 1 | 1 | 1 | 1 | 1 | 0
Front-end async handling (figuring it out) | done
Back-end database specification defined | done | 1 | 1 | 1 | 1 | 1 | 0
Back-end minimum viable product impl | done | 1 | 1 | 0
Front-end to Back-end connection impl | In Progress | 10 | 4 | 7 | 5 | 3 | 2 | 2 | 2
Back-end database timer cleanup impl | done | 3 |  |  |  | 3 | 0
Multiplayer Game Start
Front-end and Back-end state sync | In Progress | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3
Multiplayer game whose turn it is
Networked communication turn checking | done | 2 | 2 | 2 | 2 | 0
Multiplayer record turn action
Networked communication action checking | done | 2 | 2 | 2 | 2 | 0
Total Hours Assigned |  | 18 | 18 | 24 | 24 | 27 | 27 | 27 | 27
Hours Remaining |  | 18 | 18 | 20 | 17 | 12 | 6 | 6 | 6
Hours Completed |  | 0 | 0 | 4 | 7 | 15 | 21 | 21 | 21
Note on A10: Task was added as this is required to keep the backend’s database small and more robust.
Note on D1: Some work was done on this day, but not enough to reduce an hour in one of the in-progress tasks.
Note on E8: Backend has enough to do basic tests with first two protocol requests.
Note on E9: There are 5 API requests that can be made to the backend via the specified protocol. Only 3 remain as of the end of Tuesday. The resulting three probably will take longer than implementing the first two due to checking and managing game state.
Note on F9: Finished implementing the fifth protocol request/response. Implementing the rest may take more time due to game logic not yet “wired in” (but symlinked from the front-end code).
Note on F12: By implementing the fifth protocol request, the front-end can request the game state from the back-end. At this point the front-end still doesn’t communicate with the back-end yet.
Note on G1: By the end of this day, all five of the protocols that the backend responds to is more or less implemented. There still needs to be some more work done, such as cleaning out stale entries from the backend’s database.
Note on G14: Backend’s database keeps track of whose turn it is in each particular game.
Note on G16: Backend checks the validity of each turn when received.
Note on H3: This task should be finished once the frontend is fully integrated with the backend.
Note on H9: This requires work on the frontend, but this week was spent only on the backend.
Note on H12: This requires some work on the frontend, but this week was only spent on the backend.