## Sheet1
Task | Status | Start Amount | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Game Logic turn implementation
Implement turn changer | Done | 1 | 1 | 1 | 0
Game logic win/lose/draw state detection
Front-end detects win/lose/draw state from back-end | Done | 2 | 2 | 2 | 0
Multiplayer Pairing
Front-end to Back-end connection impl | Done | 2 | 2 | 2 | 0
Front-end handling of Back-end connection | Done | 7 | 4 | 2 | 0
Front-end proper disconnect handling | Done | 2 |  |  |  |  | 0
Multiplayer Game Start
Front-end and Back-end state sync | Done | 3 | 3 | 2 | 0
Total Hours |  | 15 | 15 | 15 | 15 | 15 | 17 | 17 | 17
Hours Remaining |  | 15 | 12 | 9 | 0 | 0 | 0 | 0 | 0
Hours Completed |  | 0 | 3 | 6 | 15 | 15 | 17 | 17 | 17
Note on A8: This is separate from the previous task because the Front-end requires thought on handling the connection since the front-end is event-based, and might not support threads due to the front-end being Rust WASM.
Note on A9: A bug was discovered where disconnecting players (by refresh or close of page) would not actually remove their entry from the back_end’s database. This task resolves this issue.
Note on B3: Starts Sprint as “In Progress” due to it being a previously blocked task.
Note on B7: Starts Sprint as “In Progress” due to it being a previously blocked task.
Note on B11: Starts Sprint as “In Progress” due to it being a previously blocked task.
Note on F1: Was stuck on the previous day, but had a breakthrough on this day that led me to push to finish up the frontend to backend connection impl.